Wall Calendar App

Project Plan

January 2026

# Executive Summary

This project plan outlines the development of a wall-mounted digital calendar application for Android e-ink devices (Boox). The calendar enables families and teams to view and manage shared schedules through an intuitive interface that supports handwriting input for quick event creation.

Key Features: Rolling 7-day calendar view, handwriting-to-text event creation, multi-provider calendar sync (Google, Microsoft, iCloud), e-ink optimized UI, and optional task tracking.

Target Platform: Boox Note Air5 C (10.3" e-ink display with EMR stylus)

Estimated Timeline: 12-16 weeks for MVP

# Project Goals

- Create a glanceable, always-visible family calendar for wall mounting

- Enable quick event creation by writing directly on calendar days

- Sync bidirectionally with cloud calendars (Google, Microsoft 365, iCloud)

- Optimize for e-ink display characteristics (contrast, refresh modes)

- Build a foundation that could support commercialization

# Technical Architecture

## Technology Stack

| Component | Technology |
| --- | --- |
| Language | Kotlin |
| UI Framework | Jetpack Compose |
| Stylus Input | Boox SDK (onyxsdk-pen) + Android Stylus APIs |
| Handwriting Recognition | Google ML Kit Digital Ink Recognition |
| Calendar Sync | Google Calendar API, Microsoft Graph API, CalDAV (iCloud) |
| Local Database | Room (SQLite) |
| E-ink Control | Boox SDK (EpdController) |
| Architecture | MVVM with Repository pattern |

## Calendar Integration Architecture

The app will support three calendar providers with different authentication mechanisms:

| Provider | Auth Method | Implementation |
| --- | --- | --- |
| Google | OAuth 2.0 | Google Sign-In SDK + Calendar REST API |
| Microsoft | OAuth 2.0 | MSAL Android + Microsoft Graph API |
| iCloud | App-Specific Password | CalDAV protocol with Basic Auth over HTTPS |

## iCloud Integration Note

Apple does not provide OAuth for iCloud Calendar. Users must generate an app-specific password from appleid.apple.com and enter it in the app. While this creates slightly more friction than Google/Microsoft OAuth, it is the standard approach used by all third-party calendar apps (DAVx5, Thunderbird, etc.).

# Development Phases

## Phase 0: Environment Setup (Week 1)

Objective: Establish development environment and validate hardware choice

- Set up Android Studio on macOS with Kotlin plugin

- Configure Boox SDK integration (onyxsdk-device, onyxsdk-pen)

- Acquire development device (Boox Page for testing or Boox Note Air5 C)

- Enable ADB debugging and deploy test APK

- Create basic "Hello World" app with e-ink refresh mode testing

Deliverable: Working dev environment with test app running on device

## Phase 1: Core Calendar UI (Weeks 2-4)

Objective: Build the primary calendar interface optimized for e-ink

- Design 7-day rolling calendar layout (high contrast for e-ink)

- Implement day cell components with event display

- Build date navigation (swipe left/right for different weeks)

- Create event detail modal/drawer

- Implement "Add Event" form with standard inputs

- Configure e-ink refresh modes (A2 for UI interactions, GC16 for full refresh)

- Set up Room database for local event storage

Deliverable: Functional offline calendar with local events

## Phase 2: Handwriting Input (Weeks 5-7)

Objective: Enable handwriting-to-text event creation

- Integrate Boox stylus SDK for pen input capture

- Build canvas component for capturing handwriting strokes

- Integrate Google ML Kit Digital Ink Recognition

- Implement "write in day cell" interaction pattern

- Add confirmation UI: show recognized text, allow correction

- Parse natural language times (e.g., "Dentist 3pm" -> event at 3:00 PM)

- Handle edge cases: poor handwriting, cancellation, multi-line input

Deliverable: Write in a day cell, see text recognized, event created

## Phase 3: Google Calendar Integration (Weeks 8-9)

Objective: Bidirectional sync with Google Calendar

- Register app in Google Cloud Console, configure OAuth consent

- Implement Google Sign-In flow

- Build Google Calendar API client (list calendars, fetch events, create events)

- Implement sync logic: pull remote changes, push local changes

- Handle conflict resolution (last-write-wins or prompt user)

- Add background sync with WorkManager

Deliverable: Calendar syncs with Google Calendar accounts

## Phase 4: Microsoft & iCloud Integration (Weeks 10-12)

Objective: Add remaining calendar providers

- Microsoft: Register app in Azure Portal, implement MSAL authentication

- Microsoft: Build Graph API client for calendar operations

- iCloud: Build CalDAV client (HTTP Basic Auth, XML parsing)

- iCloud: Create credential entry UI with clear instructions for app-specific passwords

- Unify event models across all providers

- Test multi-account scenarios (e.g., Google work + iCloud personal)

Deliverable: Full multi-provider calendar sync working

## Phase 5: Polish & Testing (Weeks 13-14)

Objective: Production-ready quality

- Comprehensive UI/UX review and refinement

- Error handling and offline resilience

- Performance optimization (startup time, sync speed, memory usage)

- Accessibility review

- Security audit (credential storage, API key handling)

- User testing with family members

- Bug fixes and edge case handling

Deliverable: Stable MVP ready for daily family use

## Phase 6: Optional Enhancements (Weeks 15-16+)

- Task/to-do list integration panel

- Weather widget

- Multiple calendar color coding

- Kiosk mode / screen lock

- Wall mount hardware selection and testing

# Hardware Recommendations

## Primary Recommendation: Boox Note Air5 C

| Specification | Details |
| --- | --- |
| Price | ~$530 USD |
| Display | 10.3" Kaleido 3 color e-ink (2480 x 1860) |
| Stylus | EMR technology (no battery needed), included |
| OS | Android 13 with Google Play |
| Storage | 64GB |
| Battery | 3700mAh (weeks of standby) |
| Connectivity | WiFi 6, Bluetooth 5.0, USB-C |

## Budget Alternative: Boox Page

7" grayscale e-ink, ~$359. Good for development testing but may be too small for wall calendar daily use.

## Premium Alternative: iPad Air + Apple Pencil

~$730 total. Best pen experience, no e-ink but simpler development. Consider if e-ink refresh limitations prove problematic during Phase 1.

# Risks and Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| E-ink refresh too slow | Poor UX for interactive elements | Use A2 fast mode for UI; fall back to iPad if unacceptable |
| Handwriting recognition accuracy | Frustrating event creation | ML Kit is proven; add confirmation step and manual correction |
| Boox SDK limited documentation | Development delays | Start with standard Android APIs; add Boox SDK incrementally |
| iCloud CalDAV complexity | Integration difficulties | Reference DAVx5 open source implementation; consider family switch to Google Calendar |
| Calendar API rate limits | Sync failures at scale | Implement incremental sync; respect quotas; cache aggressively |

# Timeline Summary

| Phase | Duration | Cumulative |
| --- | --- | --- |
| Phase 0: Environment Setup | 1 week | Week 1 |
| Phase 1: Core Calendar UI | 3 weeks | Week 4 |
| Phase 2: Handwriting Input | 3 weeks | Week 7 |
| Phase 3: Google Calendar | 2 weeks | Week 9 |
| Phase 4: Microsoft & iCloud | 3 weeks | Week 12 |
| Phase 5: Polish & Testing | 2 weeks | Week 14 |
| Phase 6: Optional Enhancements | 2+ weeks | Week 16+ |

Total MVP Timeline: 12-14 weeks

This assumes part-time development (~15-20 hours/week). Full-time effort could compress to 6-8 weeks.

# Recommended Next Steps

- Order development device: Boox Page ($359) for initial testing, or commit to Note Air5 C ($530)

- Set up Android Studio: Install on macOS, configure Kotlin, add Compose dependencies

- Validate e-ink UX: Build simple test app to evaluate refresh modes before committing to full development

- Decide on iCloud approach: Evaluate if app-specific password UX is acceptable, or consider migrating family calendar to Google

- Begin Phase 0: Environment setup and first deployment to device